## Sheet1
Feature	User Story	Priorities	Sprint	Story Point	Duration (in hours)
Web
Login	2- As an administrator, I want to login to the system so that I can do my work	1	1	2	8
Registration & verification	1- As a guest user, I want to register my self to the system so that I can access web-site's features	2	1	1	4
Registration & verification	2- As a guest user, I must validate and authenticate myself to the system so that I can verify my identity	3	1	13	52
Login	1- As a subscriber user, I want to login to the website so that I can use web-site's features	4	1	2	8
List Categories	1- As a subscriber user, I want to list all categories so that I can browse categories	5	1	2	8
Post new content	1- As a subscriber user, I want to post new contents about missing so that it’s displayed in categories	6	1	1	4
Search for missing/lost	2- As a subscriber user, I want to upload image of the lost so that I find the nearest match	7	1	8	32
Search for missing/lost	2- As a subscriber user, I want to specify descriptions of missing/lost so that I find the nearest match	8	1	5	20
Authenticate items	1- As a subscriber user, I must authenticate items by (serial number, distinctive attributes, …) so that it’s verified as (mine, found by me)	9	1	3	12
Find best match on new post	1- As a subscriber user, I want to find best match of a new post on posting	10	1	2	8
Secured Surveillanced communication channel	1- As a subscriber user, I want to contact other subscriber user securely	11	2	21	84
Secured Surveillanced communication channel	2- As a content moderator, I want to participate in the ongoing communications between subscribed users	12	2	5	20
Update status	1- As a subscriber user, I want to update status of missing/lost to found	13	2	1	4
Update status	2- As a System administrator, I want to update from missing/lost to found based on subscriber feedback	14	2	1	4
dashboard	5- As a site administrator, I want to crud on posts, comments, tips, users	15	1	2	8
dashboard	6- As a content moderator, I want to moderate posts, comments	16	1	2	8
dashboard	1- As a post office administrator, I want to update status of missing/lost	17	2	1	4
dashboard	2- As a post office administrator, I want to insert new contents about items	18	2	2	8
dashboard	3- As a ministry of interior administrator, I want to update status of missing/lost	19	2	1	4
dashboard	4- As a ministry of interior administrator, I want to post new contents about found people/cars	20	2	2	8
Homepage	1- As a user[ guest, subscriber, administrators ], I want to navigate homepage	21	2	3	12
Success stories	1- As a user[ guest, subscriber, administrators ], I want to navigate previous success stories	22	2	2	8
Helpful tips	1- As a user[ guest, subscriber, administrators ], I want to navigate Helpful tips	23	2	2	8
Helpful tips	2- As a subscriber user, I want to comment on helpful tips	24	2	2	8
Statistics	1- As a [ post office, ministry of interior ], I want to use statistics	25	2	5	20
Registration & verification	3- As a system administrator, I want to register other administrator/moderator	26	2	2	8

Technical Work	1-Learning TypeScripte		1	8	32

Mobile Application